## Module creation
No | Module | ER | Select | Insert | Update | Delete | Print Table | Row Print
1 | Material
2 | Supplier
3 | Quatation Request
4 | Quatation Management
5 | Purchase Order
6 | Material Receive Note
7 | Supply Payment
8 | Product
9 | Product Material
10 | Product Batch
11 | Product Order
12 | Customer
13 | Customer Order
14 | Customer Invoice
15 | Area
16 | Sales Rep
17 | Deliver Vehicle
18 | Payment
19 | Dasboard
20 | Sign up
21 | Log in
22 | Privilages
Report Generating
23 | Prouction Report
24 | Sales Report
25 | Customer Order Report
26 | Daily Income Report

## Projet logs
Iteration | Module | Completed Date | Supervisor meeting | Client Meeting
1 | Material | 24/3/2024
| Supplier | 21/3/2024
Quatation Request
Quatation Management
2 | Purchase Order
Material Receive Note
Supply Payment
3 | Product
Product Material
Product Batch
Product Order
4 | Customer
Customer Order
Customer Invoice
| Area | 24/3/2024
Sales Rep
| Deliver Vehicle | 27/3/2024
Payment
Dasboard
Sign up
Log in
Privilages
5 | Prouction Report
Sales Report
Customer Order Report
Daily Income Report